## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | Milestone 1: Environment Setup & Pipeline Design | Must Have | Docker, Apache Airflow, VS Code | Vaibhavi | Done
Sprint 2 | Sprint 2 | US-02 | Milestone 2: Data Cleaning & Transformation | Must Have | Python, Pandas | Vaibhavi | Done
Sprint 3 | Sprint 3 | US-03 | Milestone 3: Orchestration & Monitoring (Airflow DAGs & Alerts) | Must Have | Apache Airflow, Gmail SMTP, Git | Vaibhavi | Done
Sprint 4 | Sprint 4 | US-04 | Milestone 4: Dashboards & Deployment | Must Have | Streamlit, GitHub | Vaibhavi | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 28 | 8 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | 1 | Environment Setup (Docker, Airflow) | 2026-03-04 | 2026-03-06 | Vaibhavi,Bhavana | Build | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | 2 | Initial Extraction Scripts | 2026-03-07 | 2026-03-09 | Vaibhavi,Bhavana | Coding | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 3 | Data Cleaning Rules | 2026-03-16 | 2026-03-17 | Vaibhavi,Bhavana | Coding | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | 4 | Pandas Transformations | 2026-03-18 | 2026-03-20 | Vaibhavi,Bhavana | Coding | Completed | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | 5 | Airflow DAG Scheduling | 2026-03-21 | 2026-03-21 | Vaibhavi,Bhavana | Coding | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | 6 | Email Alerts (SMTP & .env) | 2026-03-22 | 2026-03-23 | Vaibhavi,Bhavana | Integration Test | Completed | 5 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | 7 | Dashboard Layout Setup,Deployment | 2026-03-25 | 2026-03-28 | Vaibhavi,Bhavana | Design | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | GitHub Codespaces memory crashed and froze during the heavy Docker Airflow build. | Closed extra VS Code tabs, waited 5 minutes, and ran docker-compose up -d in detached mode.
Sprint 1 | Day 4 | Initial data extraction scripts had hardcoded local file paths, causing errors on different machines. | Refactored the Python scripts to use relative paths so they work for both team members.
Sprint 2 | Day 14 | Unsure of the best approach to handle null/blank values in the raw dataset. | Discussed with team and implemented Pandas .dropna() and .fillna() rules for data cleaning.
Sprint 3 | Day 21 | Airflow UI showed "Invalid or unsafe next URL" (502 Bad Gateway) due to Codespaces proxy redirect. | Modified the URL manually and added AIRFLOW__WEBSERVER__ENABLE_PROXY_FIX=True to the .env file.
Sprint 3 | Day 22 | Gmail SMTP was failing to send alerts because Docker couldn't read the password properly. | Added the exact variable GMAIL_APP_PASSWORD to the .env file and restarted Docker containers.
Sprint 3 | Day 23 | Almost pushed our sensitive Gmail App Password to the public GitHub repository. | Created a .gitignore file using the terminal and added .env to it before staging files.
Sprint 3 | Day 23 | Git push was rejected due to divergent branches (GitHub had a README we didn't have locally). | Ran git config pull.rebase false and git pull origin main --no-edit to merge before pushing.
Sprint 4 | Day 26 | Encountered a crash | used Fuzzy Matching in Python to handle messy CSV headers.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-03-04 | 2026-03-13 | Vaibhavi, Bhavana | Testing Docker memory limits earlier in Codespaces. | Ignoring warning logs during initial environment setup. | Collaborating closely on the initial data extraction scripts. | Adjusted Codespaces resources to prevent crashes during Docker build.
2 | Sprint 2 | 2026-03-16 | 2026-03-22 | Vaibhavi, Bhavana | Documenting Pandas transformation logic clearly. | Hardcoding local file paths in the scripts. | Writing efficient data cleaning rules for missing values. | Implemented relative paths so the code works on both our machines.
3 | Sprint 3 | 2026-03-23 | 2026-03-25 | Vaibhavi, Bhavana | Running git pull before doing a git push to avoid conflicts. | Forgetting to hide sensitive files (like .env) before pushing to GitHub. | Helping each other debug complex Airflow HTTP proxy errors. | Added .env to .gitignore and successfully merged our branches.
4 | Sprint 4 | 2026-03-26 | 2026-03-30 | Vaibhavi, Bhavana | Using dynamic "fuzzy logic" for column mapping to prevent sudden data parsing errors. | Assuming local environments match cloud servers | Focusing on business value by refining UI elements | Added requirements.txt for Streamlit Cloud, implemented fuzzy matching for columns, and deployed dashboard.